NeurIPS 2026 — Team Onboarding Brief M7: Modality-Adaptive SNN with Cross-Modal Continual Learning Deadline: May 6, 2026 ¦ 15 days remaining ¦ CONFIDENTIAL — TEAM ONLY

# 1. Team & Responsibilities

| Name | Institution | Role | Assigned Task |
| --- | --- | --- | --- |
| Blessing Effiong | Saint Louis University | Lead — Architecture, Writing, Coordination | M7 model, paper, submission |
| Junaid Rehman | Independent Researcher | DVS-Gesture Dataset & Experiments | DVS-Gesture loader + T3 training |
| Somshubhra Roy | NC State University | Baselines & Ablation Experiments | EWC + Joint Training baselines |
| Minju Kim | Indiana University | Analysis & Figures | Gate analysis + publication figures |
| Isaac Nkrumah | Saint Louis University | Energy Analysis & Paper Review | SynOps energy + paper proofreading |

# 2. What Has Been Done (Papers 1 & 2)

## Paper 1 — NICE 2026 (Accepted, Poster with Proceedings)

Title: Memory-Augmented SNNs for Neuromorphic Vision: Supervised Contrastive Engrams

Key finding: Supervised Contrastive Learning (SCL) applied to SNNs creates stable, class-separable spike-derived representations called engrams. Combined with Modern Hopfield Networks, this achieves 97.68% on N-MNIST with strong energy efficiency (~603x vs ANN).

Status: Accepted. Presented. Published in proceedings.

## Paper 2 — IEEE Computer (Under Review, Minor Revisions)

Title: Modality-Dependent Memory Mechanisms in Cross-Modal Neuromorphic Computing

Key finding: A five-model ablation (M1–M5) across N-MNIST and SHD revealed a critical result: Hopfield networks excel on visual tasks (+0.96pp vs baseline) but degrade on auditory tasks (−6.01pp vs baseline). HGRN provides balanced cross-modal performance. The Hopfield–HGRN asymmetry is 21.53pp — this is the central empirical discovery that motivates the entire current paper.

The 21.53pp Hopfield–HGRN asymmetry is the scientific engine of this entire research arc. Everything in Paper 3 (NeurIPS) is a direct architectural response to that finding.

Confirmed M1–M5 results (referenced in Paper 3 as prior work):

| Model | N-MNIST (%) | SHD (%) | Avg (%) | Key Component |
| --- | --- | --- | --- | --- |
| M1 — Baseline (no SCL) | 96.77 | 80.04 | 88.41 | CrossEntropy only |
| M2 — + SCL | 96.72 | 82.16 ⭐ | 89.44 | + Contrastive engrams |
| M3 — + Hopfield | 97.68 ⭐ | 76.15 ⚠️ | 86.92 | + Associative memory |
| M4 — + HGRN | 97.48 | 80.08 | 88.78 | + Temporal gating |
| M5 — + Both | 97.58 | 76.94 | 87.26 | Hopfield + HGRN |

Revision deadline: May 4, 2026. Three required changes: (1) SHD-20 ablation without remapping, (2) clarify efficiency claims as lower-bound estimates, (3) remove "ANNs" from abstract + improve Figure 1. This revision runs in parallel with Paper 3.

# 3. What We Are Doing Now (Paper 3 — NeurIPS 2026)

Deadline: May 6, 2026 (11:59pm AoE = May 7, 12:00 UTC). 15 days.

Core claim: M7 is the first architecture to perform cross-modal continual learning across three heterogeneous neuromorphic sensory domains — vision (N-MNIST), audio (SHD), and motion (DVS-Gesture) — with near-zero catastrophic forgetting and strong forward transfer.

## 3.1 M7 Architecture (Built, Tested, Running)

M7 is a unified SNN that extends the best M1–M5 components with two new contributions:

- Adaptive memory gate: a 512→128→2 MLP with Softmax that learns to weight Hopfield vs HGRN per input. Motivated by the Paper 2 asymmetry — the gate should learn w_hop≈1.0 for visual inputs and higher w_hgrn for audio inputs.

- Embedding replay buffer: reservoir-sampled 512-d SCL embeddings per class (~100 KB total). Inspired by hippocampal indexing theory — compressed traces rather than raw spike replay (~80 MB).

- Per-task heads: separate LayerNorm→Linear per task, preventing cross-task gradient interference while sharing all representation layers.

## 3.2 Confirmed Two-Task Results (N-MNIST → SHD, 3 seeds each)

| Condition | N-MNIST after T2 | SHD after T2 | Forgetting F | Fwd Transfer |
| --- | --- | --- | --- | --- |
| M7-NoReplay | 97.71 ± 0.08% | 78.00 ± 1.68% | 0.01 ± 0.02pp | 72.87 ± 1.56pp |
| M7+Replay (ours) | 97.72 ± 0.02% | 77.33 ± 0.71% | 0.00 ± 0.02pp | 72.20 ± 0.81pp |

Key insight: Near-zero forgetting (≈0.01pp) emerges from per-task heads + SCL representations — without any explicit regularisation. Replay's primary contribution is gate specialisation: w_hgrn grows from 0.050 to 0.112 during SHD training with replay (seed 123), vs. w_hgrn=0.000 throughout without replay. This validates the Paper 2 prediction that HGRN is preferable for audio.

# 4. The Tri-Modal Extension (NeurIPS Requirement)

Two-task evaluation is insufficient for NeurIPS. We need three tasks with genuinely different sensory statistics. The sequential protocol extends to:

| Task | Dataset | Modality | Classes | Input Shape |
| --- | --- | --- | --- | --- |
| T1 | N-MNIST | Visual — digit recognition | 10 | [B, 25, 2, 34, 34] |
| T2 | SHD (Spiking Heidelberg Digits) | Audio — speech recognition | 20 | [B, 100, 1, 1, 700] |
| T3 | DVS-Gesture (IBM Research) | Visual Motion — gesture recognition | 11 | [B, T, 2, 128, 128] → pool to 34×34 |

DVS-Gesture rationale: reuses the Conv2D visual backbone (same polarity-based event format as N-MNIST), adds a third genuinely distinct modality (dynamic motion vs. static spatial patterns), dataset is small (~1000 samples) so training is fast, and Junaid has existing loader code.

## 4.1 Architecture Change for T3

Minimal. Add to TASKS dict and let ModuleDict create the new head automatically:

TASKS = { 'nmnist': {'num_classes': 10, 'type': 'visual'}, 'shd': {'num_classes': 20, 'type': 'audio'}, 'dvs': {'num_classes': 11, 'type': 'visual_motion'}, # NEW }

DVS-Gesture backbone: reuses SNN_Backbone (Conv2D) with adaptive spatial pooling if frames are 128×128. One line of code:

if H != 34: x = nn.functional.adaptive_avg_pool2d( x.view(B*T, C, H, W), (34, 34) ).view(B, T, C, 34, 34)

# 5. Experiment Assignments — Who Runs What

⚠️ CRITICAL: All experiments must save results to HuggingFace Hub after every seed. RunPod instances will be terminated if funding lapses. Never trust local storage alone.

## Blessing — M7 Core Experiments (Days 1–4)

Notebook: NeurIPS2026_M7_clean.ipynb (already built, upload to new RunPod instance)

| Experiment | Runtime | Priority | Output File |
| --- | --- | --- | --- |
| M7-NoReplay + M7+Replay (3 seeds each, 2-task) | ≈3 hrs | 🔴 P1 | cl_results.csv |
| Tri-modal: N-MNIST → SHD → DVS-Gesture | ≈5 hrs | 🔴 P1 | cl_trimodal_results.csv |
| Gate fix experiment (λ_gate_audio = 0.1) | ≈1.5 hrs | 🟡 P2 | gate_fix_results.csv |

## Junaid — DVS-Gesture Integration (Days 1–3)

Contact Blessing by EOD today to confirm DVS-Gesture loader status. This is the critical path item for tri-modal.

| Task | Deadline | Priority | Deliverable |
| --- | --- | --- | --- |
| Provide DVS-Gesture DataLoader producing [B, T, 2, H, W] tensors | Day 2 | 🔴 P1 | dvs_loader.py |
| Confirm: 11 gesture classes, train/test split sizes | Day 2 | 🔴 P1 | Message in group chat |
| Run DVS-Gesture single-task M7 smoke test (1 seed) | Day 3 | 🔴 P1 | Accuracy + loss to group chat |

If DVS-Gesture loader is not ready by Day 3, fall back to SSC-35 (Spiking Speech Commands). Blessing already has the SSC loader. Signal early if there are problems.

## Somshubhra — Baselines (Days 3–6)

Run on Kaggle or your own compute. Use NeurIPS_new_cells.py (Cells 37-38) from the shared notebook.

| Experiment | Runtime | Priority | Output File |
| --- | --- | --- | --- |
| EWC baseline: sequential N-MNIST → SHD, 3 seeds, λ=5000 | ≈2 hrs | 🔴 P1 | ewc_results.csv |
| Joint Training upper bound: simultaneous N-MNIST + SHD, 3 seeds | ≈2 hrs | 🔴 P1 | joint_results.csv |
| M7 component ablation: NoSCL, FixedGate, SharedHead (3 seeds each) | ≈3 hrs | 🟡 P2 | ablation_results.csv |

## Minju — Gate Analysis & Figures (Days 6–9)

Load checkpoints from the shared HuggingFace repo and produce publication-ready figures.

| Task | Deadline | Priority | Deliverable |
| --- | --- | --- | --- |
| Gate weight evolution plot (w_hgrn trajectory across 3 tasks, replay vs no-replay) | Day 8 | 🔴 P1 | fig2_gate_specialisation.pdf |
| Tri-modal 3×3 accuracy matrix heatmap | Day 8 | 🔴 P1 | fig3_accuracy_matrix.pdf |
| Main CL bar chart (M7 vs EWC vs Joint Training, forgetting + accuracy) | Day 9 | 🔴 P1 | fig1_cl_main.pdf |
| Forward transfer analysis across 3 tasks | Day 9 | 🟡 P2 | fig4_forward_transfer.pdf |

## Isaac — Energy Analysis & Paper Review (Days 7–12)

| Task | Deadline | Priority | Deliverable |
| --- | --- | --- | --- |
| SynOps energy analysis (0.9 pJ/spike) for all 3 task backbones | Day 9 | 🟡 P2 | energy_results.json |
| Full paper proofread — every number vs. CSV, every citation, checklist | Day 12 | 🔴 P1 | Annotated PDF to Blessing |

# 6. 15-Day Timeline

| Days | Focus | Key Tasks | Who |
| --- | --- | --- | --- |
| 1–2 | Infrastructure +Core Experiments | New RunPod + HF backup. Start M7-NoReplay/Replay. DVS loader from Junaid. | Blessing, Junaid |
| 3–4 | DVS Integration +Baselines Start | Integrate T3 DVS-Gesture. Run tri-modal experiment. EWC + Joint Training start. | Blessing, Junaid, Somshubhra |
| 5–6 | Baselines Complete +Ablation | EWC + Joint Training 3 seeds done. Ablation study running. Gate fix running. | Somshubhra, Blessing |
| 7–9 | Paper Writing +Figures | Update all tables. Write tri-modal results. Generate all 4 figures. Energy analysis. | Blessing, Minju, Isaac |
| 10–11 | Polish + Review | Full proofread. Check every number. Verify anonymous submission. NeurIPS checklist. | All |
| 12–13 | Submission Prep | Final PDF. Supplementary material. OpenReview upload test. | Blessing |
| 14 | SUBMIT | Submit to OpenReview before 11:59pm AoE (= May 7 12:00 UTC). | Blessing |
| 15 | Buffer | Something will go wrong. This day absorbs it. | All |

# 7. Critical Rules for This Paper

RULE 1: Never put a number in the paper that is not in a CSV file. No estimates. No approximations from training logs. Every number must be traceable to a confirmed experiment.

RULE 2: Save results to HuggingFace after every seed. The RunPod instance will be terminated without warning if funding lapses. We already lost data once.

RULE 3: Anonymous submission. No author names anywhere in the paper PDF. Self-citations use \citep{anon2026modality} format. Supplementary PDFs of Papers 1 & 2 must be anonymised.

RULE 4: Report test accuracy, not validation accuracy. The SHD val/test gap is ~15-19pp. Validation is for early stopping only. All tables report test set numbers.

RULE 5: The forgetting claim is zero, not 100% reduction. Both NoReplay and Replay achieve ~0.00pp forgetting. Do not say "replay reduces forgetting by 100%." The honest claim is that replay enables gate specialisation.

# 8. Key Numbers to Know

Every team member should memorise these before writing or discussing the paper.

| Metric | Value | Source |
| --- | --- | --- |
| Hopfield–HGRN asymmetry on SHD (Paper 2) | 21.53pp | M3 vs M4, confirmed |
| M7 N-MNIST (independent) | 97.74 ± 0.04% | cl_results.csv |
| M7 SHD (independent) | 82.21 ± 0.41% | cl_results.csv |
| M7 forgetting (NoReplay) | 0.01 ± 0.02pp | cl_results.csv |
| M7 forgetting (Replay) | 0.00 ± 0.02pp | cl_results.csv |
| Forward Transfer FWT | 72.87 ± 1.56pp | cl_results.csv |
| SHD zero-shot after T1 | ≈5% | cl_results.csv |
| Gate w_hgrn with replay (seed 123) | 0.112 at convergence | training logs |
| Replay buffer size | ≈100 KB | analytical: 10×50×512×4B |
| Raw spike replay equivalent | ≈80 MB | analytical |
| Efficiency vs raw replay | ≈800× smaller | analytical |
| M7 total parameters | 6,333,308 | model count |

# 9. Shared Resources

- GitHub repo: beffiong1/cross-modal-neuromorphic-system — push all code changes

- HuggingFace: upload all result CSVs and checkpoints after every seed

- Overleaf: NeurIPS2026_M7_submission.tex + references.bib (Blessing shares link)

- Clean notebook: NeurIPS2026_M7_clean.ipynb — upload to your compute environment

- This document: share with all team members, treat as the source of truth

Questions? Message Blessing directly. Do not make architectural decisions without discussing first. All changes to the model code must be communicated to the full team before running experiments.

NeurIPS 2026 Submission — CONFIDENTIAL — Team Use Only